## Master
Project Card | [22 empty] | Type | Forecast | [50 empty] | Actual
Project Owner | Portfolio Lead | Project Number | Contract Number | Account Number | Project Name | Customer Logo | Project Fund ($) | Project Fund (AED) | Total Hours (Without Contingency) | Total Hours (With Contingency) | Overall Rating |  | NB Expenses |  | Orig Bid |  |  |  | EAC (Estimate at closure) |  |  |  | Quarter | Q1-26 |  |  | Q2-26 |  |  | Q3-26 |  |  | Q4-26 |  |  | Q1-27 |  |  | Q2-27 |  |  | Q3-27 |  |  | Q4-27 |  |  | Q1-28 |  |  | Q2-28 |  |  | Q3-28 |  |  | Q4-28 |  |  | Q1-29 |  |  | Q2-29 |  |  | Q3-29 |  |  | Q4-29 |  |  | Q1-30 |  |  | Q2-26 |  |  | Q3-26 |  |  | Q4-26 |  |  | Q1-27 |  |  | Q2-27 |  |  | Q3-27 |  |  | Q4-27
[11 empty] | Current Quarter | Prevoius Quarter | Total Expenses | Utilized Expenses | Hours | Revenue | Cost | Margin | Hours | Revenue | Cost | Margin | Revenue | 0 |  |  | 0 |  |  | 144998.7057 |  |  | 150031 |  |  | 185667 |  |  | 19367.2004 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 144998.7057 |  |  | 150031 |  |  | 131463 |  |  | 0 |  |  | 0 |  |  | 0
[23 empty] | Invoicing | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 250170.2997 |  |  | 25017.03 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[23 empty] | Month | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Amr Hossam | Khaled Selim | 400379228 | 301018758 | 11105402 | A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | #VALUE! | 499932 | 1834750.44 | 6194 | 7744 | 90 | 90 | 23123 | 0 | 6194 | 500340 | 262894 | 52.54% | 7481 | 500340 | 238492 | 47.67% | Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42349.6116 | 47772.4277 | 59909.2066 | 59392.7479 | 72045.9855 | 54228.1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58876.2893 | 73595.3616 | 52678.7851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58876.2893 | 73595.3616 | 52678.7851 | 0 | 0 | 0 | 0 | 0 | 0 | 42349.6116 | 47772.4277 | 59909.2066 | 59392.7479 | 72045.9855 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Overall Rating |  | NB Expenses |  | Orig Bid |  |  |  | EAC (Estimate at closure) |  |  |  | Invoicing Month: Quarter; 0 Jun: Q1-26; 0 Sep: Q2-26; 0 Dec: Q3-26; 0 Mar: Q4-26; 250170.2997 Jun: Q1-27; 25017.03 Sep: Q2-27; 0 Dec: Q3-27; 0 Mar: Q4-27; 0 Jun: Q1-28; 0 Sep: Q2-28; 0 Dec: Q3-28; 0 Mar: Q4-28; 0 Jun: Q1-29; 0 Sep: Q2-29; 0 Dec: Q3-29; 0 Mar: Q4-29; 0 Jun: Q1-30; 0 Sep: Q2-26; 0 Dec: Q3-26; 0 Mar: Q4-26; 0 Jun: Q1-27; 0 Sep: Q2-27; 0 Dec: Q3-27; 0 Mar: Q4-27
[11 empty] | Current Quarter | Prevoius Quarter | Total Expenses | Utilized Expenses | Hours | Revenue | Cost | Margin | Hours | Revenue | Cost | Margin | Invoicing Month: Revenue; 0 Jun: 0; 0 Sep: 0; 0 Dec: 0; 0 Mar: 426684; 250170.2997 Jun: 150262; 25017.03 Sep: 40000; 0 Dec: 0; 0 Mar: 0; 0 Jun: 0; 0 Sep: 0; 0 Dec: 0; 0 Mar: 0; 0 Jun: 0; 0 Sep: 0; 0 Dec: 0; 0 Mar: 0; 0 Jun: 0; 0 Sep: 0; 0 Dec: 0; 0 Mar: 426684; 0 Jun: 0; 0 Sep: 0; 0 Dec: 0; 0 Mar: 0
[23 empty] | Invoicing | 0 |  |  | 0 |  |  | 0 |  |  | 225153.2698 |  |  | 0 |  |  | 93000 |  |  | 496000 |  |  | 31000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 225153.2698 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[23 empty] | Month | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Manal Mourad | Khaled Selim | 400398318 | 301020783 | 15426325 | A8XQVP_FP_Solution+_Workload Migration | #VALUE! | 620000 | 2277880 | 4888 | 5592 | 90 | 90 | 117453 | 0 | 3914 | 620000 | 309299 | 49.89% | 5592 | 620000 | 269619 | 43.49% | Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18290 | 121210 | 287184 | 50000 | 50262 | 50000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18290 | 121210 | 287184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Overall Rating |  | NB Expenses |  | Orig Bid |  |  |  | EAC (Estimate at closure) |  |  |  | Invoicing Month: Quarter; 0 Jun: Q1-26; 0 Sep: Q2-26; 0 Dec: Q3-26; 225153.2698 Mar: Q4-26; 0 Jun: Q1-27; 93000 Sep: Q2-27; 496000 Dec: Q3-27; 31000 Mar: Q4-27; 0 Jun: Q1-28; 0 Sep: Q2-28; 0 Dec: Q3-28; 0 Mar: Q4-28; 0 Jun: Q1-29; 0 Sep: Q2-29; 0 Dec: Q3-29; 0 Mar: Q4-29; 0 Jun: Q1-30; 0 Sep: Q2-26; 0 Dec: Q3-26; 225153.2698 Mar: Q4-26; 0 Jun: Q1-27; 0 Sep: Q2-27; 0 Dec: Q3-27; 0 Mar: Q4-27
[11 empty] | Current Quarter | Prevoius Quarter | NB Expenses | Utilized Expenses | Hours | Revenue | Cost | Margin | Hours | Revenue | Cost | Margin | Invoicing Month: Revenue; 0 Jun: 0; 0 Sep: 0; 0 Dec: 0; 225153.2698 Mar: 199850; 0 Jun: 72991; 496000 Dec: 0; 31000 Mar: 141158.2213; 0 Jun: 240692; 0 Sep: 239184; 0 Dec: 356816; 0 Mar: 398063; 0 Jun: 474448; 0 Sep: 468868; 0 Dec: 463891; 0 Mar: 388185; 0 Jun: 24355; 0 Sep: 0; 0 Dec: 0; 225153.2698 Mar: 199850; 0 Jun: 47250; 0 Sep: 0; 0 Dec: 0; 0 Mar: 0
[23 empty] | Invoicing | 0 |  |  | 0 |  |  | 0 | [5 empty] | 150000 | [11 empty] | 0 | [11 empty] | 0 | [11 empty] | 0 |  |  | 0 |  |  | 0 | [5 empty] | 150000 |  |  | 0 |  |  | 0 |  |  | 0
[23 empty] | Month | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Omar Hefnawy | Ali Omar | 400406275 | 301025567 | 15426325 | A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | #VALUE! | 3500000 | 12859000 | 37,865 | 46414 | 90 | 90 | 95000 | 0 | 46416 | 3500000 | 2018591 | 42.3% | 46416 | 3500000 | 2188019 | 37.5% | Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66616.6667 | 66616.6667 | 66616.6667 | 12818 | 45092 | 15081 |  |  |  | 0 | 0 | 0 | 47052.7404 | 47052.7404 | 47052.7404 | 80230.6667 | 80230.6667 | 80230.6667 | 79728 | 79728 | 79728 | 118938.6667 | 118938.6667 | 118938.6667 | 132687.6667 | 132687.6667 | 132687.6667 | 158149.3333 | 158149.3333 | 158149.3333 | 156289.3333 | 156289.3333 | 156289.3333 | 154630.3333 | 154630.3333 | 154630.3333 | 129395 | 129395 | 129395 | 8118.3333 | 8118.3333 | 8118.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199850 | 9800 | 47250 | -9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Overall Rating |  | NB Expenses |  | Orig Bid |  |  |  | EAC (Estimate at closure) |  |  |  | Invoicing Month: Quarter; 0 Jun: Q1-26; 0 Sep: Q2-26; 0 Dec: Q3-26; 0 Mar: Q4-26; 150000 Jun: Q1-27; 150000 Sep: Q2-27; 150000 Dec: Q3-27; 150000 Mar: Q4-27; 0 Jun: Q1-28; 0 Sep: Q2-28; 0 Dec: Q3-28; 0 Mar: Q4-28; 0 Jun: Q1-29; 0 Sep: Q2-29; 0 Dec: Q3-29; 0 Mar: Q4-29; 0 Jun: Q1-30; 0 Sep: Q2-26; 0 Dec: Q3-26; 0 Mar: Q4-26; 150000 Jun: Q1-27; 0 Sep: Q2-27; 0 Dec: Q3-27; 0 Mar: Q4-27
[11 empty] | Current Quarter | Prevoius Quarter | NB Expenses | Utilized Expenses | Hours | Revenue | Cost | Margin | Hours | Revenue | Cost | Margin | Invoicing Month: Revenue; 0 Jun: 55983.6845; 0 Sep: 845725.0911; 0 Dec: 431684.619; 0 Mar: 358919.0955; 150000 Jun: 249000; 150000 Sep: 150000; 150000 Dec: 0; 150000 Mar: 150000; 0 Jun: 150000; 0 Sep: 150000; 0 Dec: 150000; 0 Mar: 150000; 0 Sep: 845725.0911; 0 Dec: 431684.619; 0 Mar: 358919.0955; 150000 Jun: 249000; 0 Sep: 0; 0 Dec: 0; 0 Mar: 0
[23 empty] | Invoicing |  |  |  | 830000 | [20 empty] | 0 | [11 empty] | 0 | [11 empty] | 0 |  |  | 830000 |  |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[23 empty] | Month | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Amr Abbasy | Khaled Selim | 400365175 | 301002795 | 15426325 | A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | #VALUE! | 3350000 | 12307900 | 40402 | 50504 | 80 | 60 | 203250 | 0 | 40402 | 3350000 | 1894536 | 43.4% | 40298 | 3350000 | 1,820,651 | 45.7% | Revenue | 0 | 0 | 55983.6845 | 247283.3835 | 338820.6875 | 259621.0201 | 98037.7792 | 170670.6399 | 162976.1999 | 115151.2751 | 114089.9731 | 129677.8473 | 83000 | 83000 | 83000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 247283.3835 | 338820.6875 | 259621.0201 | 98037.7792 | 170670.6399 | 162976.1999 | 115151.2751 | 114089.9731 | 129677.8473 | 83000 | 83000 | 83000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Projects TimeSheet
Project Name | A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD
Sum of Quantity | Column Labels
| Jan | Feb | Mar | Apr | May | Jun |  |  |  | Jun Total | Jul |  |  |  |  | Jul Total | Aug | Aug Total | Grand Total
[6 empty] | 05-Jun | 12-Jun | 19-Jun | 26-Jun |  | 03-Jul | 10-Jul | 17-Jul | 24-Jul | 31-Jul |  | 07-Aug
Row Labels
ahmed.a.said@oracle.com |  | 80 | [16 empty] | 80
ahmed.aa.attia@oracle.com |  |  | 32 | 32 | 16 | [13 empty] | 80
ahmed.h.hassan@oracle.com | 32 | 160 | 64 | 64 | 68 | [13 empty] | 388
ahmed.labib@oracle.com | 32 | 160 | 112 | 112 | 28 | [13 empty] | 444
ahmed.n.nasr@oracle.com | 24 | 112 | [16 empty] | 136
ajith.thota@oracle.com | [5 empty] | 24 | 40 | 40 | 40 | 144 | 32 | 32 | 40 | 40 | 40 | 184 |  |  | 328
ali.omar.hasan@oracle.com | 12 | 48 | [16 empty] | 60
amr.h.hossam@oracle.com |  |  |  |  | 28 | 28 | 28 | 28 | 28 | 112 | 28 | 28 | 28 | 28 | 28 | 140 |  |  | 280
anirban.basu@oracle.com |  | 80 | 28 | 76 | 100 | 20 | 12 | 20 | 20 | 72 | 20 | 20 | 20 | 20 | 20 | 100 | 8 | 8 | 464
asmaa.i.ibrahim@oracle.com | 32 | 160 | 96 | 96 | 120 | 32 | 32 | 32 | 32 | 128 | 32 | 32 | 32 | 32 | 32 | 160 |  |  | 792
balaji.ketti@oracle.com |  | 40 | [16 empty] | 40
basma.elsaify@oracle.com |  | 48 | [16 empty] | 48
ebrahim.youssri@oracle.com |  | 80 | [16 empty] | 80
karim.kh.hassan@oracle.com |  | 80 | [16 empty] | 80
khaled.selim@oracle.com |  |  | 48 | [15 empty] | 48
khulode.emad.el-din@oracle.com | [6 empty] | 20 | 20 |  | 40 | [8 empty] | 40
kishore.babu.katta@oracle.com | 32 | 160 | 80 | 80 | 100 | 20 | 20 | 20 | 20 | 80 | 20 | 20 | 20 | 20 | 20 | 100 |  |  | 632
kyrillos.nagy@oracle.com | [5 empty] | 8 | 8 | 8 | 8 | 32 | 8 | 8 | 8 | 8 |  | 32 |  |  | 64
manisekaran.seetharaman@oracle.com |  |  | 32 | 32 | 16 | [13 empty] | 80
mayank.y.raj@oracle.com |  |  |  | 40 | 192 | 40 | 40 | 40 | 40 | 160 | 40 | 40 | 40 | 40 | 40 | 200 |  |  | 592
menna.allah.shaaban@oracle.com | 32 | 112 | [16 empty] | 144
mohamed.m.ragab@oracle.com | 32 | 160 | [16 empty] | 192
mostafa.mahmoud@oracle.com |  | 135.9 | [16 empty] | 135.9
moustafa.ahmed@oracle.com | 32 | 160 | 28 | [15 empty] | 220
rawan.ismail@oracle.com |  |  | 56 | 56 | 60 | [13 empty] | 172
reem.a.amin@oracle.com |  | 80 | [16 empty] | 80
tarek.abo.ali@oracle.com | 16 | 120 | [16 empty] | 136
vijayalakshmi.jayakumar@oracle.com |  |  | 80 | 152 | 200 | 32 | 40 | 40 | 40 | 152 | 40 | 40 | 40 | 40 | 40 | 200 | 16 | 16 | 800
vikram.v.batchu@oracle.com |  | 40 | [16 empty] | 40
Grand Total | 276 | 2015.9 | 656 | 740 | 928 | 204 | 240 | 248 | 228 | 920 | 220 | 220 | 228 | 228 | 220 | 1116 | 24 | 24 | 6675.9
Project Name | A8XQVP_FP_Solution+_Workload Migration
Sum of Quantity | Column Labels
| <06/03/2026 | Mar |  |  |  | Mar Total | Apr |  |  |  | Apr Total | May |  |  |  | May Total | Grand Total
Row Labels |  | 06-Mar | 13-Mar | 20-Mar | 27-Mar |  | 03-Apr | 10-Apr | 17-Apr | 24-Apr |  | 01-May | 08-May | 15-May | 22-May
ahmed.aa.atef@oracle.com |  | 16 | 40 | 40 | 40 | 136 | 40 |  |  |  | 40 |  | 40 | 80 |  | 120 | 296
ahmed.aa.attia@oracle.com | [12 empty] | 28 | 80 |  | 108 | 108
ahmed.fahim@oracle.com | [6 empty] | 40 | 32 | 32 | 24 | 128 | 40 | 24 | 40 |  | 104 | 232
amr.elabbasy@oracle.com | [7 empty] | 40 | 48 |  | 88 | [5 empty] | 88
amr.h.hossam@oracle.com |  |  |  |  | 32 | 32 | 32 |  | 32 | 32 | 96 | 40 | 40 | 80 |  | 160 | 288
balaji.ketti@oracle.com | [13 empty] | 48 |  | 48 | 48
hany.ali@oracle.com |  | 16 | 16 | 24 |  | 56 | 40 | 24 | 24 | 24 | 112 | 40 | 80 | 80 |  | 200 | 368
jesus.alonso@oracle.com | [12 empty] | 80 | 64 | 16 | 160 | 160
khaled.k.abbady@oracle.com | [8 empty] | 40 | 72 | 112 | 80 | 24 | 24 |  | 128 | 240
khaled.selim@oracle.com |  |  |  |  | 24 | 24 | 24 | 36 | 36 | 36 | 132 | 36 | 36 | 36 |  | 108 | 264
manal.mourad@oracle.com |  |  |  |  | 32 | 32 | 32 |  | 32 | 32 | 96 | 32 | 32 | 80 |  | 144 | 272
mina.maher@oracle.com |  |  |  |  | 32 | 32 | 32 | 32 | 48 | 40 | 152 | 48 | 40 | 40 |  | 128 | 312
mohamed.abdel.sabour@oracle.com |  |  |  |  | 24 | 24 | 40 | 50 | 40 | 46 | 176 | 40 |  | 8 |  | 48 | 248
rajesh.budakoti@oracle.com | [6 empty] | 40 | 40 |  | 32 | 112 |  | 8 |  |  | 8 | 120
raju.vishwakarma@oracle.com | [6 empty] | 24 | 24 | 24 | 24 | 96 | 24 | 80 | 80 |  | 184 | 280
rudi.v.van.der.westhuizen@oracle.com | [12 empty] | 32 |  |  | 32 | 32
vikram.v.batchu@oracle.com | [13 empty] | 48 |  | 48 | 48
(blank)
Grand Total |  | 32 | 56 | 64 | 184 | 336 | 344 | 278 | 356 | 362 | 1340 | 380 | 544 | 788 | 16 | 1728 | 3404
Project Name | A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig
Sum of Quantity | Column Labels
| May |  |  |  | May Total | Jun | Jul | Grand Total
| 08-May | 15-May | 22-May | 29-May
Row Labels
ahmed.abdel.aziz@oracle.com | 30 | 80 |  |  | 110 |  |  | 110
ahmed.k.kassem@oracle.com | 40 | 40 |  |  | 80 |  |  | 80
ahmed.labib@oracle.com | 30 | 80 |  |  | 110 |  |  | 110
ahmed.ma.maher@oracle.com | 30 | 40 |  |  | 70 |  |  | 70
ahmed.moheb@oracle.com | 30 | 80 |  |  | 110 |  |  | 110
amr.h.hossam@oracle.com | 30 |  |  |  | 30 |  |  | 30
amr.osama@oracle.com | 30 | 80 |  |  | 110 |  |  | 110
ashish.ac.sharma@oracle.com | 80 | 80 |  |  | 160 |  |  | 160
asmaa.i.ibrahim@oracle.com | 32 | 32 |  |  | 64 |  |  | 64
deepak.n.gupta@oracle.com | 80 | 80 |  |  | 160 |  |  | 160
francesco.sabiu@oracle.com | 80 | 80 |  |  | 160 |  |  | 160
harikaran.s@oracle.com | 80 | 72 |  |  | 152 |  |  | 152
harshal.devkar@oracle.com | 80 | 80 |  |  | 160 |  |  | 160
himanshu.n.nayak@oracle.com | 80 | 72 |  |  | 152 |  |  | 152
kalyan.vunnam@oracle.com | 80 | 80 |  |  | 160 |  |  | 160
khaled.r.rady@oracle.com |  | 40 |  |  | 40 |  |  | 40
koustubh.kanetkar@oracle.com | 80 | 80 |  |  | 160 |  |  | 160
marwa.g.gamal@oracle.com |  | 0 | 0 | 0 | 0 | 112 | 144 | 256
md.shareef@oracle.com | 80 | 72 |  |  | 152 |  |  | 152
omar.hefnawy@oracle.com |  | 40 | 56 | 56 | 152 | 74 | 150 | 376
rawan.ismail@oracle.com | 16 | 12 |  |  | 28 |  |  | 28
sampat.achary@oracle.com | 80 | 80 |  |  | 160 |  |  | 160
sharavanakumar.k.k.v@oracle.com | 80 | 80 |  |  | 160 |  |  | 160
srinivasan.venkat.raman@oracle.com | 80 | 72 |  |  | 152 |  |  | 152
Grand Total | 1228 | 1452 | 56 | 56 | 2792 | 186 | 294 | 3272
Project Name | A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD
Sum of Quantity | Column Labels
| <8/8/2025 | 2025 | [6 empty] | 2025 Total | 2026 | [7 empty] | 2026 Total | Grand Total
|  | Qtr3 |  | Qtr3 Total | Qtr4 |  |  | Qtr4 Total |  | Qtr1 | Qtr2 |  |  | Qtr2 Total | Qtr3 |  | Qtr3 Total
Row Labels |  | Aug | Sep |  | Oct | Nov | Dec |  |  |  | Apr | May | Jun |  | Jul | Aug
abhinaw.jaiswal@oracle.com |  |  |  |  | 160 | 152 | 152 | 464 | 464 | 256 | [7 empty] | 256 | 720
ahmed.a.said@oracle.com |  |  |  |  | 160 | 56 |  | 216 | 216 | [9 empty] | 216
ahmed.aa.atef@oracle.com |  |  | 320 | 320 |  | 80 |  | 80 | 400 | [9 empty] | 400
ahmed.aa.attia@oracle.com |  |  | 160 | 160 | 186 | 98 |  | 284 | 444 | [9 empty] | 444
ahmed.abdel.aziz@oracle.com |  |  |  |  | 64 | 48 |  | 112 | 112 | [9 empty] | 112
ahmed.ah.mostafa@oracle.com |  | 24 |  | 24 |  |  |  |  | 24 | [9 empty] | 24
ahmed.fahim@oracle.com |  |  | 160 | 160 | 344 |  |  | 344 | 504 | 96 | 40 | 82 |  | 122 |  |  |  | 218 | 722
ahmed.g.ghareeb@oracle.com |  |  |  |  | 48 | 112 | 24 | 184 | 184 | 217 | [7 empty] | 217 | 401
ahmed.h.hassan@oracle.com |  | 20 | 160 | 180 | 64 | 88 | 88 | 240 | 420 | 216 | [7 empty] | 216 | 636
ahmed.k.kassem@oracle.com |  |  |  |  | 40 |  |  | 40 | 40 | 40 | 80 | 160 |  | 240 |  |  |  | 280 | 320
ahmed.labib@oracle.com |  |  | 160 | 160 | 200 | 160 |  | 360 | 520 | [9 empty] | 520
ahmed.ma.maher@oracle.com |  |  | 160 | 160 | 160 |  |  | 160 | 320 | [9 empty] | 320
ahmed.moheb@oracle.com |  | 80 | 296 | 376 |  | 80 |  | 80 | 456 | [9 empty] | 456
amir.mawla@oracle.com |  |  | 224 | 224 | 120 | 160 |  | 280 | 504 | [9 empty] | 504
amira.ibrahim@oracle.com |  |  |  |  | 88 |  | 24 | 112 | 112 | 272 | [7 empty] | 272 | 384
amr.elabbasy@oracle.com |  | 40 | 160 | 200 | 156 | 140 | 108 | 404 | 604 | 312 | 56 | 112 | 112 | 280 | 28 |  | 28 | 620 | 1224
amr.h.hossam@oracle.com |  |  |  |  | 96 |  |  | 96 | 96 | [9 empty] | 96
ashish.ab.sharma@oracle.com |  |  |  |  | 168 | 160 | 152 | 480 | 480 | 496 | 152 | 200 | 160 | 512 | 200 | 16 | 216 | 1224 | 1704
ashish.ac.sharma@oracle.com |  | 104 |  | 104 | 56 | 112 |  | 168 | 272 | [9 empty] | 272
asmaa.murad@oracle.com |  |  |  |  | 160 |  |  | 160 | 160 | [9 empty] | 160
ayman.s.shawky@oracle.com |  |  |  |  | 80 |  |  | 80 | 80 | [9 empty] | 80
deepak.n.gupta@oracle.com |  |  |  |  | 56 | 112 |  | 168 | 168 | [9 empty] | 168
habiba.e.el.matboly@oracle.com |  |  | 320 | 320 | 344 | 320 | 75 | 739 | 1059 | 378 | 128 | 96 | 80 | 304 | 72 |  | 72 | 754 | 1813
hany.ali@oracle.com |  | 72 | 160 | 232 | 48 | 64 | 64 | 176 | 408 | 280 | [7 empty] | 280 | 688
harshal.devkar@oracle.com |  |  |  |  | 56 | 128 |  | 184 | 184 | [9 empty] | 184
hazem.k.khaled@oracle.com |  |  |  |  | 200 | 24 |  | 224 | 224 | [9 empty] | 224
hemant.shrimali@oracle.com |  |  |  |  | 56 | 128 |  | 184 | 184 | [9 empty] | 184
ishwar.patil@oracle.com |  |  |  |  | 80 | 160 |  | 240 | 240 | [9 empty] | 240
karim.kh.hassan@oracle.com |  |  |  |  | 160 |  |  | 160 | 160 | [9 empty] | 160
khaled.r.rady@oracle.com |  |  | 160 | 160 | 78 | 64 |  | 142 | 302 | 120 | [7 empty] | 120 | 422
khaled.selim@oracle.com |  | 80 | 104 | 184 | 100 | 64 | 64 | 228 | 412 | 160 | [7 empty] | 160 | 572
khloud.samir@oracle.com |  |  |  |  | 40 |  | 40 | 80 | 80 | 248 | [7 empty] | 248 | 328
kumaresan.kaliyamoorthy@oracle.com | [9 empty] | 224 | 160 | 168 | 152 | 480 | 200 |  | 200 | 904 | 904
manal.mourad@oracle.com |  | 72 | 160 | 232 | 64 | 88 | 96 | 248 | 480 | 216 | [7 empty] | 216 | 696
menna.allah.shaaban@oracle.com |  |  |  |  | 40 | 40 |  | 80 | 80 | [9 empty] | 80
mina.maher@oracle.com |  | 64 | 320 | 384 | 344 | 320 | 59 | 723 | 1107 | 452 | 152 |  | 104 | 256 | 120 |  | 120 | 828 | 1935
moaz.tawfik@oracle.com |  | 56 |  | 56 |  |  |  |  | 56 | [9 empty] | 56
mohamed.abdel.sabour@oracle.com | [9 empty] | 24 |  | 72 |  | 72 |  |  |  | 96 | 96
mohamed.m.osama@oracle.com |  |  | 160 | 160 | 236 | 160 | 89 | 485 | 645 | 498 | 160 | 169 |  | 329 |  |  |  | 827 | 1472
mostafa.ashraf.farouk@oracle.com | [9 empty] | 120 | [7 empty] | 120 | 120
osama.s.salah@oracle.com | [9 empty] | 240 | 80 | 160 |  | 240 |  |  |  | 480 | 480
piyush.deshpande@oracle.com |  |  |  |  | 40 | 20 |  | 60 | 60 | [9 empty] | 60
raju.vishwakarma@oracle.com |  |  |  |  | 168 | 160 | 152 | 480 | 480 | 496 | 160 | 192 | 160 | 512 | 200 | 16 | 216 | 1224 | 1704
rana.ramy@oracle.com | [9 empty] | 216 | 152 | 152 | 104 | 408 | 120 |  | 120 | 744 | 744
sampat.achary@oracle.com |  |  |  |  | 56 | 120 |  | 176 | 176 | [9 empty] | 176
sanjeev.s.gupta@oracle.com |  |  | 40 | 40 |  |  |  |  | 40 | [9 empty] | 40
satyam.k.kumar@oracle.com |  |  | 160 | 160 | 168 | 160 | 152 | 480 | 640 | 448 | 120 | 192 | 60 | 372 | 100 | 8 | 108 | 928 | 1568
sirish.vegad@oracle.com | [9 empty] | 32 | [7 empty] | 32 | 32
soujanya.havanagi@oracle.com |  | 72 |  | 72 |  |  |  |  | 72 | [9 empty] | 72
sudhalakshmi.gavirni@oracle.com | [6 empty] | 80 | 80 | 80 | [9 empty] | 80
wael.hamouda@oracle.com |  | 80 | 104 | 184 |  | 16 |  | 16 | 200 | [9 empty] | 200
yomna.salama@oracle.com |  | 80 | 240 | 320 | 344 | 320 | 59 | 723 | 1043 | 405 | 160 | 176 |  | 336 |  |  |  | 741 | 1784
ziad.diaa@oracle.com |  |  |  |  | 80 |  |  | 80 | 80 | 304 | 120 | 24 |  | 144 |  |  |  | 448 | 528
(blank)
Grand Total |  | 844 | 3728 | 4572 | 5108 | 3914 | 1478 | 10500 | 15072 | 6766 | 1720 | 1955 | 932 | 4607 | 1040 | 40 | 1080 | 12453 | 27525

## Milestones
Project Name | Sno | Milestone | Percentage | Fee in AED | Fee in $ | Project Currency | Expected Date To Submit the Certificate | Certificate Status | Invoice Status | Notes
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 1 | Kick-Off Meeting Notes | 10% | 183625 | 50034.0599 | AED | 2026-03-27 | Submitted | Paid
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 2 | Project Plan | 15% | 275437.5 | 75051.0899 | AED | 2026-03-27 | Submitted | Paid
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 3 | Submission of Technical Configuration Document for Enterprise Analytics - Finance - Ledger 1 | 10% | 183625 | 50034.0599 | AED | 2026-03-27 | Submitted | Paid
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 4 | Submission of Technical Configuration Document for Enterprise Analytics - Finance - Ledger 2 | 10% | 183625 | 50034.0599 | AED | 2026-06-19 | Submitted | Not Paid Yet
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 5 | Submission of Technical Configuration Document for Enterprise Analytics - Finance - Ledger 3 | 10% | 183625 | 50034.0599 | AED | 2026-06-19 | Submitted | Not Paid Yet
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 6 | Submission of Technical Configuration Document for Enterprise Analytics - SCM - Ledger 1 | 5% | 91812.5 | 25017.03 | AED | 2026-03-27 | Submitted | Paid
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 7 | Submission of Technical Configuration Document for Enterprise Analytics - SCM - Ledger 2 | 5% | 91812.5 | 25017.03 | AED | 2026-06-19 | Submitted | Not Paid Yet
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 8 | Submission of Technical Configuration Document for Enterprise Analytics - HR - Operating Unit 1 | 5% | 91812.5 | 25017.03 | AED | 2026-03-27 | Submitted | Paid
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 9 | Submission of Technical Configuration Document for Enterprise Analytics - HR - Operating Unit 2 | 5% | 91812.5 | 25017.03 | AED | 2026-06-19 | Submitted | Not Paid Yet
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 10 | Submission of Technical Configuration Document for Enterprise Analytics - HR - Operating Unit 3 | 5% | 91812.5 | 25017.03 | AED | 2026-06-19 | Submitted | Not Paid Yet
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 11 | Submission of Functional Requirement Document for Oracle Data Warehouse for Maximo | 5% | 91812.5 | 25017.03 | AED | 2026-04-15 | Submitted | Not Paid Yet | Delayed, expected new date 15-6-2026
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 12 | Submission of Technical Design Document for Oracle Data Warehouse for Maximo | 5% | 91812.5 | 25017.03 | AED | 2026-04-24 | Submitted | Not Paid Yet | Delayed, expected new date 15-6-2027
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 13 | Submission of UAT Issue log tracker for Enterprise Analytics and Oracle Data Warehouse for Maximo | 5% | 91812.5 | 25017.03 | AED | 2026-08-13 | Not Yet Submitted | Not Paid Yet
A7ZNQZ_ FP_TECH TAQA Fusion Analytics Accelerator CLOUD | 14 | Submission of PPS Issue log tracker for Enterprise Analytics and Oracle Data Warehouse for Maximo | 5% | 91812.5 | 25017.03 | AED | 2026-09-23 | Not Yet Submitted | Not Paid Yet
A8XQVP_FP_Solution+_Workload Migration | 1 | Completion of deliverable D02: Project Management Plan including Governance setup. | 10% | 227726 | 62000 | AED | 2026-04-30 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 2 | Completion of deliverable D05: Data Collection and Discovery Workshops | 10% | 227726 | 62000 | AED | 2026-04-30 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 3 | Completion of deliverable D09: High level Architecture covering Target Network Design, Target Security principles, Supporting Infrastructure. | 5% | 113863 | 31000 | AED | 2026-04-30 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 4 | Completion of deliverable D10: Candidate Application List (CAL) for Each Move Groups (Tools extract). | 5% | 113863 | 31000 | AED | 2026-05-09 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 5 | Completion of deliverable D19: Execution of Trail Run. | 5% | 113863 | 31000 | AED | 2026-05-09 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 6 | Completion of deliverable D21: Technical Verification document for first (1st) batch of fifty (50) migrated workloads. | 10% | 227726 | 62000 | AED | 2026-05-16 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 7 | Completion of deliverable D22: Technical Verification document for second (2nd) batch of fifty (50) migrated workloads. | 10% | 227726 | 62000 | AED | 30/05//2026 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 8 | Completion of deliverable D23: Technical Verification document for third (3rd) batch of fifty (50) migrated workloads. | 10% | 227726 | 62000 | AED | 2026-06-13 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 9 | Completion of deliverable D24: Technical Verification document for fourth (4th) batch of fifty (50) migrated workloads. | 10% | 227726 | 62000 | AED | 2026-06-27 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 10 | Completion of deliverable D25: Technical Verification document for fifth (5th) batch of fifty (50) migrated workloads. | 10% | 227726 | 62000 | AED | 2026-07-11 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 11 | Completion of deliverable D26: Technical Verification document for sixth (6th) batch of up to forty-seven (47) migrated workloads. | 10% | 227726 | 62000 | AED | 2026-08-08 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8XQVP_FP_Solution+_Workload Migration | 12 | Completion of deliverable D27: Hypercare and Handover | 5% | 113863 | 31000 | AED | 2026-08-22 | Not Yet Submitted | Not Paid Yet | Project Delayed by 3 months due to Pre-Sales Discussion
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 1 | Project Kick-off Meeting | 4.286% | 550950 | 150000 | USD | 2026-05-05 | Submitted | Partially paid
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 2 | Project Management Plan | 2.571% | 330570 | 90000 | USD | 2026-08-07 | Submitted | Not Paid Yet
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 3 | Discovery & Analysis Document – DRCC Workloads | 2.571% | 330570 | 90000 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 4 | High-Level Design (HLD) | 3% | 385665 | 105000 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 5 | Foundation Setup – OCI Landing Zone | 3% | 385665 | 105000 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 6 | Low-Level Design (LLD) | 2.857% | 367300 | 100000 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 7 | Technical Verification Documents MG1 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 8 | Technical Verification Documents MG2 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 9 | Technical Verification Documents MG3 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 10 | Technical Verification Documents MG4 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 11 | Technical Verification Documents MG5 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 12 | Technical Verification Documents MG6 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 13 | Technical Verification Documents MG7 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 14 | Technical Verification Documents MG8 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 15 | Technical Verification Documents MG9 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 16 | Technical Verification Documents MG10 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 17 | Technical Verification Documents MG11 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 18 | Technical Verification Documents MG12 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 19 | Technical Verification Documents MG13 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 20 | Technical Verification Documents MG14 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 21 | Technical Verification Documents MG15 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 22 | Technical Verification Documents MG16 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 23 | Technical Verification Documents MG17 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 24 | Technical Verification Documents MG18 | 4.301% | 552883.1579 | 150526.3158 | USD
A8YLGG_FP_COMBO_CSS_OMANTEL_Workload Mig | 25 | Technical Verification Documents MG19 | 4.301% | 552883.1579 | 150526.3158 | USD
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 1 | On Contract Signature |  | 1229450 | 335000 | USD | 25/11/2025 | Submitted | Paid
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 2 | Completion of deliverable D02: Project Management Plan including Governance setup. |  | 605550 | 165000 | USD | 25/11/2025 | Submitted | Paid
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 3 | Completion of deliverable D05: Data Collection and Discovery Workshops |  | 605550 | 165000 | USD | 2026-09-04 | Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 4 | Completion of deliverable D09: High level Architecture covering Target Network Design, Target Security principles, Supporting Infrastructure. |  | 605550 | 165000 | USD | 2026-09-04 | Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 5 | Completion of deliverable D10: Candidate Application List (CAL) for Each Move Groups (Tools extract). |  | 605550 | 165000 | USD | 2026-10-07 | In Progress | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 6 | Completion of deliverable D21: Execution of Trail Run. |  | 605550 | 165000 | USD | 2026-10-06 | Completed | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 7 | Completion of deliverable D23: Technical Verification document for 1st batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/7/2026 | In Progress | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 8 | Completion of deliverable D24: Technical Verification document for 2nd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/8/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 9 | Completion of deliverable D25: Technical Verification document for 3rd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/8/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 10 | Completion of deliverable D26: Technical Verification document for 4th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/8/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 11 | Completion of deliverable D27: Technical Verification document for 5th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/9/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 12 | Completion of deliverable D28: Technical Verification document for 6th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/9/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 13 | Completion of deliverable D29: Technical Verification document for 7th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/9/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 14 | Completion of deliverable D30: Technical Verification document for 8th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/10/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 15 | Completion of deliverable D31: Technical Verification document for 9th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/10/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 16 | Completion of deliverable D32: Technical Verification document for 10th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/11/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 17 | Completion of deliverable D33: Technical Verification document for 11th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/11/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 18 | Completion of deliverable D34: Technical Verification document for 12th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/11/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 19 | Completion of deliverable D35: Technical Verification document for 13th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/12/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 20 | Completion of deliverable D36: Technical Verification document for 14th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/12/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 21 | Completion of deliverable D37: Technical Verification document for 15th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/12/2026 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 22 | Completion of deliverable D38: Technical Verification document for 16th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/1/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 23 | Completion of deliverable D39: Technical Verification document for 17th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/1/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 24 | Completion of deliverable D40: Technical Verification document for 18th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/1/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 25 | Completion of deliverable D41: Technical Verification document for 19th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 28/2/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 26 | Completion of deliverable D42: Technical Verification document for 20th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 28/2/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 27 | Completion of deliverable D43: Technical Verification document for 21st batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 28/2/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 28 | Completion of deliverable D44: Technical Verification document for 22nd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/3/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 29 | Completion of deliverable D45: Technical Verification document for 23rd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/3/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 30 | Completion of deliverable D46: Technical Verification document for 24th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/3/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 31 | Completion of deliverable D47: Technical Verification document for 25th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/4/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 32 | Completion of deliverable D48: Technical Verification document for 26th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/4/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 33 | Completion of deliverable D49: Technical Verification document for 27th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/4/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 34 | Completion of deliverable D50: Technical Verification document for 28th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/5/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 35 | Completion of deliverable D51: Technical Verification document for 29th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/5/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 36 | Completion of deliverable D52: Technical Verification document for 30th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/5/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 37 | Completion of deliverable D53: Technical Verification document for 31st batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/6/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 38 | Completion of deliverable D54: Technical Verification document for 32nd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/6/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 39 | Completion of deliverable D55: Technical Verification document for 33rd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | 30/6/2027 | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 40 | Completion of deliverable D56: Technical Verification document for 34th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 41 | Completion of deliverable D57: Technical Verification document for 35th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 42 | Completion of deliverable D58: Technical Verification document for 36th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 43 | Completion of deliverable D59: Technical Verification document for 37th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 44 | Completion of deliverable D60: Technical Verification document for 38th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 45 | Completion of deliverable D61: Technical Verification document for 39th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 46 | Completion of deliverable D62: Technical Verification document for 40th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 47 | Completion of deliverable D63: Technical Verification document for 41st batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 48 | Completion of deliverable D64: Technical Verification document for 42nd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 49 | Completion of deliverable D65: Technical Verification document for 43rd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 50 | Completion of deliverable D66: Technical Verification document for 44th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 51 | Completion of deliverable D67: Technical Verification document for 45th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 52 | Completion of deliverable D68: Technical Verification document for 46th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 53 | Completion of deliverable D69: Technical Verification document for 47th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 54 | Completion of deliverable D70: Technical Verification document for 48th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 55 | Completion of deliverable D71: Technical Verification document for 49th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 56 | Completion of deliverable D72: Technical Verification document for 50th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 57 | Completion of deliverable D73: Technical Verification document for 51st batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 58 | Completion of deliverable D74: Technical Verification document for 52nd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 59 | Completion of deliverable D75: Technical Verification document for 53rd batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 60 | Completion of deliverable D76: Technical Verification document for 54th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 61 | Completion of deliverable D77: Technical Verification document for 55th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 62 | Completion of deliverable D78: Technical Verification document for 56th batch of 100 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 63 | Completion of deliverable D79: Technical Verification document for 57th batch of 103 migrated workloads. |  | 137625 | 37500 | USD | Change Scope Document | Not Yet Submitted | Not Paid Yet
400365175 - A7XFJB_ FP TECH E & Enterprise Cloud - Sole Proprietorship LLC-Alloy CLOUD | 64 | Hypercare and Handover |  | 192675 | 52500 | USD | TBD | Not Yet Submitted | Not Paid Yet

## PIC
Project Owner | Pic | Portfolio Lead | Pic
Karim Khaled | #VALUE! | Ali Omar | #VALUE!
Amr Hossam | #VALUE! | Ali Omar | #VALUE!
Manal Mourad | #VALUE! | Khaled Selim | #VALUE!
Omar Hefnawy | #VALUE!
Amr Abbasy | #VALUE! | Amr Abbasy | #VALUE!